Odoo 17 Delivery Management Module

Traccar GPS Integration — Comprehensive Implementation Plan

Abdelrehman Elhaj  |  Khatwa Tech  |  June 2026

# 1. Overview

This document is the end-to-end implementation plan for integrating Traccar as the GPS backbone of the custom delivery_management Odoo 17 Community module. It replaces iQ4Mobility as the primary tracking provider and covers every layer: infrastructure, Odoo data models, the FastAPI bridge service, the driver mobile experience, and the customer live-tracking page.

| Parameter | Value |
| --- | --- |
| Module name | delivery_management (Odoo 17 Community addon) |
| GPS provider | Traccar (self-hosted, OCI Compute) |
| Bridge service | FastAPI (Python 3.11, OCI Compute) |
| Routing API | Google Maps Directions API |
| Customer tracking | Odoo portal.mixin — tokenised public URL |
| Target timeline | 14 weeks (5 phases) |
| Total dev effort | ~290 hours |

# 2. System Architecture

## 2.1  Data flow summary

Position data flows in one direction: Traccar driver app → Traccar server → FastAPI webhook bridge → delivery.vehicle (Odoo) → ir.cron ETA engine → customer tracking page. No GPS data is stored in the bridge; it is stateless and immediately forwards to Odoo via JSON-RPC.

## 2.2  Infrastructure components

| Component | Hosting | Notes |
| --- | --- | --- |
| Odoo 17 Community | OCI VM / AWS EC2 | Existing deployment — no change required |
| Traccar Server | OCI Compute (same VPC) | Runs as a JAR on port 8082; H2 embedded DB sufficient for <50 vehicles |
| FastAPI bridge | OCI Compute (same VM as Traccar) | Single Python process; systemd service; ~200 lines |
| PostgreSQL 15 | Existing Odoo DB | No new database required |
| Google Maps API | External SaaS | Directions API for ETA; Maps JS for customer page |

## 2.3  Odoo data models

Six models cover the full delivery lifecycle. GPS-specific fields are added to delivery.vehicle and consumed by delivery.stop via the ETA engine.

| Model | Purpose & key fields |
| --- | --- |
| delivery.order | Core order: mode (pickup/delivery), sale.order link, scheduled date, tracking_token, state |
| delivery.trip | A truck's daily run grouping multiple orders. Links to vehicle, driver, stops |
| delivery.stop | One physical stop: partner address, sequence, eta (Datetime), status, photo ids |
| delivery.vehicle | Truck registry: plate, traccar_device_id, last_lat, last_lng, gps_updated |
| delivery.driver | Driver profile linked to res.users; mobile access permissions |
| delivery.photo | Binary attachment per stop, timestamped, geo-tagged |

# 3. Traccar Server Setup

## 3.1  Installation on OCI

- Provision OCI Compute instance (VM.Standard.E4.Flex, 1 OCPU / 4 GB RAM minimum). Open port 8082 (TCP) in the security list.

- Download and extract Traccar:

wget https://github.com/traccar/traccar/releases/latest/download/traccar-linux-64.zip

unzip traccar-linux-64.zip -d /opt/traccar && chmod +x /opt/traccar/traccar.sh

- Create /opt/traccar/conf/traccar.xml with database and web configuration (H2 embedded for <50 vehicles; migrate to PostgreSQL for larger fleets):

<properties>

<entry key='database.driver'>org.h2.Driver</entry>

<entry key='database.url'>jdbc:h2:/opt/traccar/data/database</entry>

<entry key='web.port'>8082</entry>

<entry key='web.origin'>*</entry>

</properties>

- Register as a systemd service and enable on boot:

sudo ln -s /opt/traccar/traccar.sh /etc/init.d/traccar

sudo systemctl enable traccar && sudo systemctl start traccar

Note: Traccar admin UI is at http://<oci-ip>:8082. Create one Odoo service account user in Traccar for the webhook integration — do not use the admin account.

## 3.2  Configuring Traccar webhooks

In the Traccar admin UI: Notifications → Add → select type 'Web Service' → set the URL to your FastAPI bridge endpoint. Enable triggers for: Position Update. This fires a POST to your bridge every time a device sends a GPS ping (typically every 5–30 seconds depending on the driver app settings).

## 3.3  Driver app setup

Drivers install the free Traccar Client app from Google Play or the App Store. Configuration required on each phone:

- Server URL: http://<oci-ip>:8082

- Device identifier: the value you enter in delivery.vehicle.traccar_device_id in Odoo (use truck plate number for clarity, e.g. 'ABC-1234')

- Frequency: set position update interval to 30 seconds for a balance of accuracy and battery life

Note: The Traccar Client app reports GPS in the background even when the phone screen is locked. This eliminates the browser-open requirement of the fallback Geolocation API approach.

# 4. FastAPI Webhook Bridge

## 4.1  Purpose

The bridge is a single-responsibility microservice: receive a Traccar position event, validate it, and forward the lat/lng to Odoo via JSON-RPC. It holds no state. If it goes down, Traccar queues events and replays them when the bridge recovers.

## 4.2  Project structure

gps_bridge/

main.py          # FastAPI app — single file

requirements.txt # fastapi, uvicorn, httpx, python-dotenv

.env             # ODOO_URL, ODOO_DB, ODOO_API_KEY, BRIDGE_SECRET

gps_bridge.service  # systemd unit file

## 4.3  Full implementation

# main.py

from fastapi import FastAPI, Request, HTTPException

from fastapi.responses import JSONResponse

import httpx, os, logging

from dotenv import load_dotenv

load_dotenv()

app = FastAPI()

log = logging.getLogger('gps_bridge')

ODOO_URL   = os.environ['ODOO_URL']

ODOO_DB    = os.environ['ODOO_DB']

ODOO_KEY   = os.environ['ODOO_API_KEY']

SECRET     = os.environ.get('BRIDGE_SECRET', '')

@app.post('/traccar/webhook')

async def receive_position(req: Request):

if SECRET and req.headers.get('X-Traccar-Secret') != SECRET:

raise HTTPException(status_code=401)

data = await req.json()

device_id = str(data.get('deviceId', ''))

pos = data.get('position', {})

lat, lng = pos.get('latitude'), pos.get('longitude')

if not device_id or lat is None or lng is None:

return JSONResponse({'status': 'skip'})

async with httpx.AsyncClient(timeout=5) as client:

await client.post(

f'{ODOO_URL}/web/dataset/call_kw',

json={

'jsonrpc': '2.0', 'method': 'call', 'id': 1,

'params': {

'model': 'delivery.vehicle',

'method': 'update_gps_position',

'args': [[device_id, lat, lng]], 'kwargs': {}

}

},

headers={'X-Openerp-Session-Id': ODOO_KEY}

)

return {'status': 'ok'}

@app.get('/health')

async def health(): return {'status': 'alive'}

## 4.4  Systemd service

[Unit]

Description=GPS Bridge (Traccar -> Odoo)

After=network.target

[Service]

WorkingDirectory=/opt/gps_bridge

EnvironmentFile=/opt/gps_bridge/.env

ExecStart=/opt/gps_bridge/venv/bin/uvicorn main:app --host 0.0.0.0 --port 8090

Restart=always

RestartSec=5

[Install]

WantedBy=multi-user.target

Note: Expose port 8090 in your OCI security list. Add BRIDGE_SECRET to .env and match it in the Traccar notification header to prevent spoofed webhook calls.

# 5. Odoo Module Implementation

## 5.1  Module scaffold

delivery_management/

__manifest__.py

__init__.py

models/

__init__.py

delivery_vehicle.py

delivery_driver.py

delivery_order.py

delivery_trip.py

delivery_stop.py

delivery_photo.py

controllers/

__init__.py

portal.py

views/

delivery_vehicle_views.xml

delivery_order_views.xml

delivery_trip_views.xml

delivery_stop_views.xml

portal_tracking.xml

data/

ir_cron.xml

security/

ir.model.access.csv

## 5.2  delivery.vehicle model

class DeliveryVehicle(models.Model):

_name = 'delivery.vehicle'

_description = 'Delivery Vehicle'

name               = fields.Char(required=True)

plate              = fields.Char()

traccar_device_id  = fields.Char(index=True)

capacity           = fields.Float()

active             = fields.Boolean(default=True)

last_lat           = fields.Float(digits=(10, 7))

last_lng           = fields.Float(digits=(10, 7))

gps_updated        = fields.Datetime(readonly=True)

@api.model

def update_gps_position(self, device_id, lat, lng):

v = self.search([('traccar_device_id','=',device_id)], limit=1)

if v:

v.write({'last_lat': lat, 'last_lng': lng,

'gps_updated': fields.Datetime.now()})

return True

## 5.3  delivery.order model (key fields)

class DeliveryOrder(models.Model):

_name = 'delivery.order'

_inherit = ['mail.thread', 'portal.mixin']

sale_order_id   = fields.Many2one('sale.order')

mode            = fields.Selection([('pickup','Pickup'),

('delivery','Delivery')])

scheduled_date  = fields.Datetime()

trip_id         = fields.Many2one('delivery.trip')

state           = fields.Selection([

('draft','Draft'),('confirmed','Confirmed'),

('in_progress','In Progress'),('done','Done'),

('failed','Failed')])

tracking_token  = fields.Char(copy=False, index=True)

next_stop_id    = fields.Many2one('delivery.stop',

compute='_compute_next_stop')

def _compute_portal_url(self):

for rec in self:

rec.portal_url = f'/delivery/track/{rec.tracking_token}'

@api.model_create_multi

def create(self, vals_list):

for vals in vals_list:

if not vals.get('tracking_token'):

vals['tracking_token'] = self.env['ir.sequence']\

.next_by_code('delivery.order.token')

return super().create(vals_list)

## 5.4  ETA cron job

# In delivery_trip.py

def _cron_refresh_etas(self):

active = self.search([('state','=','in_progress')])

for trip in active:

v = trip.vehicle_id

if not v.last_lat:

continue

stops = trip.stop_ids.filtered(

lambda s: s.status not in ('delivered','failed')

).sorted('sequence')

if not stops:

continue

eta = self._call_directions_api(

v.last_lat, v.last_lng,

stops[0].partner_lat, stops[0].partner_lng

)

stops[0].write({'eta': eta})

trip.order_ids.filtered(

lambda o: o.next_stop_id == stops[0]

).message_post(body=f'ETA updated: {eta}')

## 5.5  ir.cron XML registration

<record id='ir_cron_refresh_etas' model='ir.cron'>

<field name='name'>Refresh delivery ETAs</field>

<field name='model_id' ref='model_delivery_trip'/>

<field name='state'>code</field>

<field name='code'>model._cron_refresh_etas()</field>

<field name='interval_number'>1</field>

<field name='interval_type'>minutes</field>

<field name='active'>True</field>

</record>

# 6. Customer Tracking Page

## 6.1  Portal controller

# controllers/portal.py

class DeliveryPortal(http.Controller):

@http.route('/delivery/track/<string:token>',

auth='public', website=True)

def track_delivery(self, token):

order = request.env['delivery.order'].sudo()\

.search([('tracking_token','=',token)], limit=1)

if not order:

return request.not_found()

return request.render(

'delivery_management.tracking_page',

{'order': order, 'vehicle': order.trip_id.vehicle_id}

)

@http.route('/delivery/track/<string:token>/poll',

auth='public', type='json')

def poll_position(self, token):

order = request.env['delivery.order'].sudo()\

.search([('tracking_token','=',token)], limit=1)

if not order:

return {}

v = order.trip_id.vehicle_id

stop = order.next_stop_id

return {

'lat':    v.last_lat,

'lng':    v.last_lng,

'eta':    stop.eta.isoformat() if stop and stop.eta else None,

'status': order.state,

'stops_remaining': len(order.trip_id.stop_ids.filtered(

lambda s: s.status not in ('delivered','failed')))

}

## 6.2  QWeb template (key JS polling block)

<t t-name='delivery_management.tracking_page'>

<div id='tracking-map' style='height:400px'></div>

<div id='eta-display'/>

<script>

const token = '<t t-esc='order.tracking_token'/>';

let marker;

function initMap() {

const map = new google.maps.Map(

document.getElementById('tracking-map'),

{zoom: 13, center: {lat: 24.68, lng: 46.72}}

);

marker = new google.maps.Marker({map});

poll();

setInterval(poll, 60000);

}

async function poll() {

const r = await fetch(`/delivery/track/${token}/poll`,

{method:'POST',

headers:{'Content-Type':'application/json'},

body: JSON.stringify({jsonrpc:'2.0',method:'call',params:{}})});

const d = (await r.json()).result;

if (d && d.lat) {

marker.setPosition({lat: d.lat, lng: d.lng});

document.getElementById('eta-display').textContent =

d.eta ? 'ETA: ' + new Date(d.eta).toLocaleTimeString() : '';

}

}

</script>

</t>

# 7. Driver Mobile View

## 7.1  Design principles

The driver view is intentionally minimal. It uses Odoo's built-in PWA capabilities — no separate React or Flutter app is needed. The Traccar Client app runs in the background handling GPS; the Odoo PWA is only for status updates and photo uploads.

- Login once — session persisted; no repeated password entry on each trip

- Home screen shows only today's stops in sequence order

- Maximum 3 taps to mark a stop: Open stop → tap status → confirm

- Photo upload uses HTML5 capture API directly from device camera

- Offline-tolerant: status and photo queue locally if connectivity drops, sync on reconnect

- All UI labels in both Arabic and English

## 7.2  Odoo controller for driver view

@http.route('/delivery/driver', auth='user', website=True)

def driver_home(self):

driver = request.env['delivery.driver'].sudo()\

.search([('user_id','=',request.env.uid)], limit=1)

if not driver:

return request.redirect('/web')

today_stops = request.env['delivery.stop'].sudo().search([

('trip_id.driver_id','=',driver.id),

('trip_id.date','=',fields.Date.today()),

('status','not in',['delivered','failed'])

], order='sequence asc')

return request.render('delivery_management.driver_home',

{'stops': today_stops})

# 8. Implementation Phases

| Phase | Weeks | Deliverables |
| --- | --- | --- |
| Phase 1 | 1–3 | Core data models (6 models), sales order button + wizard, delivery calendar, module scaffold, ir.sequence for tracking tokens |
| Phase 2 | 3–6 | Manager Kanban dashboard, route optimisation (Google Maps Directions), trip management, driver mobile view (Odoo PWA) |
| Phase 3 | 6–9 | Traccar server deployment, FastAPI bridge, delivery.vehicle GPS fields, ir.cron ETA engine, customer tracking page, SMS/email notifications |
| Phase 4 | 9–11 | Reporting (on-time rate, driver performance, failed-delivery reasons), XLSX export, UAT bug fixes, query optimisation |
| Phase 5 | 11–14 | Staging deployment to OCI/AWS, driver training, Arabic UI review, go-live support, technical documentation |

# 9. Effort Estimate

| Work package | Estimate (hrs) |
| --- | --- |
| Discovery & architecture | 20 |
| Core models + sales order integration | 40 |
| Manager dashboard + delivery calendar | 35 |
| Route optimisation (Google Maps API) | 25 |
| Driver mobile view (Odoo PWA) | 30 |
| Traccar setup + FastAPI bridge | 20 |
| GPS fields + ir.cron ETA engine | 20 |
| Customer tracking page (portal + polling) | 25 |
| SMS / email notifications + chatter | 15 |
| Reporting & XLSX export | 20 |
| Testing, UAT, bug fixes | 30 |
| Deployment & documentation | 20 |
| Total estimated | ~300 hrs |

# 10. Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Driver forgets to open Traccar Client app before trip | Medium | Configure Traccar Client to auto-start on phone boot; add pre-trip checklist to driver PWA home screen |
| Google Maps API billing exceeds budget | Low | Cap daily API calls via GCP quotas; cache route results per trip (recalculate only when stop order changes) |
| Traccar server OCI downtime | Low | Traccar Client queues positions locally and replays on reconnect; add OCI health check + auto-restart via systemd |
| Client delays providing GPS device IDs / truck plate data | Medium | Block trip dispatch in Odoo if traccar_device_id is empty — enforced at model level, not just UI |
| UAT scope creep extending Phase 4 | High | Demo end of each phase; get sign-off on core flows before Phase 4 begins; track change requests separately |
| Odoo JSON-RPC session expiry on API user | Low | Use Odoo API keys (not session cookies) for the bridge; keys do not expire |

# 11. Security Checklist

- Traccar webhook endpoint protected by shared secret header (X-Traccar-Secret)

- FastAPI bridge runs on internal OCI subnet — not publicly exposed; Nginx reverse proxy with HTTPS if public access needed

- Odoo API user for the bridge has permissions scoped to delivery.vehicle only (read + write last_lat/last_lng)

- Customer tracking tokens are generated via ir.sequence — not guessable sequential IDs

- Tracking page is auth='public' but returns no PII — only lat/lng, ETA, and status

- Driver portal enforces res.users login — no anonymous driver access

- All GPS coordinates stored in Odoo PostgreSQL — no third-party cloud storage

# 12. Testing Plan

## 12.1  Unit tests (Python)

- delivery.vehicle.update_gps_position: valid device ID, unknown device ID, missing lat/lng

- delivery.trip._cron_refresh_etas: active trip with GPS data, active trip without GPS data, completed trip (should skip)

- delivery.order tracking_token generation: uniqueness across 1000 records

## 12.2  Integration tests

- POST to /traccar/webhook with valid payload → confirm delivery.vehicle updated in Odoo

- POST to /traccar/webhook with invalid secret → 401 returned, Odoo not called

- GET /delivery/track/<token> with valid token → 200, correct template

- GET /delivery/track/<token> with invalid token → 404

- POST /delivery/track/<token>/poll → JSON with lat, lng, eta, status

## 12.3  UAT scenarios

- Full trip lifecycle: Sales order → dispatch → driver marks stops → customer tracks → delivery complete

- GPS signal loss mid-trip: driver goes underground, signal recovers — ETA resumes correctly

- Failed delivery: driver marks stop as failed → customer page shows failed state → manager notified

- Arabic UI: all driver PWA labels render correctly in RTL layout on Android

# 13. Immediate Next Steps

- Provision OCI Compute instance and deploy Traccar server (Day 1 — ~2 hours)

- Create delivery_management module scaffold and commit to GitHub repo odoo17-delivery-sa

- Implement delivery.vehicle and delivery.order models with GPS fields (Week 1)

- Build and deploy FastAPI bridge on the same OCI instance as Traccar (Week 1–2)

- Assign traccar_device_id values to all client vehicles and run first end-to-end GPS test (Week 2 — requires client input)

- Demo Phase 1 to client at end of Week 3 before proceeding to dashboard work

Abdelrehman Elhaj  |  a.Elhaj@proptech.sa  |  Khatwa Tech

Confidential — prepared for client review